## R1 I1
Task # | Iteration | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | R1: I1 | 01. Login/Registration | 1.08 | Reset Password | Implement core functionality and entitlements crosscuts | 2022-02-18 | 2022-02-25 | 100% | Hemaswi
2 |  |  | 1.08 | Reset Password | Implement text field that will allow user to add email address | 2022-02-18 | 2022-02-19 | 100% | Hemaswi
3 |  |  | 1.08 | Reset Password | Implement text field that will allow user to input their name | 2022-02-18 | 2022-02-19 | 100% | Hemaswi
4 |  |  | 1.08 | Reset Password | Implement text field that will allow user to input a new password | 2022-02-18 | 2022-02-19 | 100% | Hemaswi
5 |  |  | 1.08 | Reset Password | Develop test cases for Reset password functionaltiy and entitlements crosscuts | 2022-02-18 | 2022-02-25 | 100% | Abhilash
6 |  |  | 1.08 | Reset Password | Execute test cases | 2022-02-18 | 2022-02-25 | 100% | Abhilash
7 |  | 03. Order & Cart Management | 3.03 | Add / Remove item(s) to cart | Implement a button that will allow a user to add an item to the cart. | 2022-02-18 | 2022-02-25 | 100% | Hemaswi
8 |  |  | 3.03 | Add / Remove item(s) to cart | Implement a button that will allow a user to remove an item from the cart. | 2022-02-18 | 2022-02-25 | 100% | Hemaswi
9 |  |  | 3.03 | Add / Remove item(s) to cart | Implement core functionality and data flow out crosscuts | 2022-02-18 | 2022-02-25 | 100% | Masha
10 |  |  | 3.03 | Add / Remove item(s) to cart | Develop test cases for functionality, GUI, and data flow out crosscuts | 2022-02-18 | 2022-02-25 | 0% | Abhilash and Brinda
11 |  |  | 3.03 | Add / Remove item(s) to cart | Execute test cases | 2022-02-18 | 2022-02-25 | 0% | Abhilash and Brinda
12 |  |  | 3.07 | Display items/total price in cart | Implement core functionality and data flow in crosscuts | 2022-02-25 | 2022-03-04 | 100% | Hemaswi and Masha
13 |  |  | 3.07 | Display items/total price in cart | Add text fields that will show items a user has ordered | 2022-02-25 | 2022-03-04 | 100% | Hemaswi and Masha
14 |  |  | 3.07 | Display items/total price in cart | Add text fields that will show price of items a user has ordered | 2022-02-25 | 2022-03-04 | 100% | Hemaswi and Masha
15 |  |  | 3.07 | Display items/total price in cart | Add dropdown box that will allow a user to increase or decrease the total number of a singular item in their order | 2022-02-25 | 2022-03-04 | 100% | Hemaswi and Masha
16 |  |  | 3.07 | Display items/total price in cart | Develop test cases for functionality, GUI, and data flow in crosscuts | 2022-02-25 | 2022-03-04 | 0% | Abhilash and Brinda
17 |  |  | 3.07 | Display items/total price in cart | Execute test cases | 2022-02-25 | 2022-03-04 | 0% | Abhilash and Brinda
18 |  |  | 3.08 | Display number of items in cart | Implement core functionality and daata flow in crosscuts | 2022-02-25 | 2022-03-04 | 100% | Hemaswi and Masha
19 |  |  | 3.08 | Display number of items in cart | Implement total amount of items in cart with text box | 2022-02-25 | 2022-03-04 | 100% | Hemaswi and Masha
20 |  |  | 3.08 | Display number of items in cart | Develop test cases for functionality, GUI, and data flow in crosscuts | 2022-02-25 | 2022-03-04 | 0% | Abhilash and Brinda
21 |  |  | 3.08 | Display number of items in cart | Execute test cases | 2022-02-25 | 2022-03-04 | 0% | Abhilash and Brinda

## R1 I2
Task # | Iteration | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | R1:I2 | 01. Login/Registration | 1.05 | Create admin account | Implemet core features and entitlements crosscut | 2022-03-04 | 2022-03-11 | 0% | Masha and Hemaswi
2 |  |  | 1.05 | Create admin account | Implement dataflow out crosscuts | 2022-03-04 | 2022-03-11 | 0% | Masha and Hemaswi
3 |  |  | 1.05 | Create admin account | Add email address text field so user can add their email address during sign up | 2022-03-04 | 2022-03-11 | 0% | Masha and Hemaswi
4 |  |  | 1.05 | Create admin account | Add password and re-enter password text fields | 2022-03-04 | 2022-03-11 | 0% | Masha and Hemaswi
5 |  |  | 1.05 | Create admin account | Add create account button | 2022-03-04 | 2022-03-11 | 0% | Masha and Hemaswi
6 |  |  | 1.05 | Create admin account | Add name text fields | 2022-03-04 | 2022-03-11 | 0% | Masha and Hemaswi
7 |  |  | 1.05 | Create admin account | Develop test cases for GUI, core functionality, and crosscuts | 2022-03-04 | 2022-03-18 | 0% | Abhilash and Brinda
8 |  |  | 1.05 | Create admin account | Execute test cases | 2022-03-04 | 2022-03-18 | 0% | Abhilash and Brinda
9 |  |  | 1.04 | Admin Login | Implemet core features and entitlements crosscut | 2022-03-04 | 2022-03-18 | 0% | Masha and Hemaswi
10 |  |  | 1.04 | Admin Login | Implement data flow in crosscuts | 2022-03-04 | 2022-03-18 | 0% | Masha and Hemaswi
11 |  |  | 1.04 | Admin Login | Add text fields for a user to add their username/email address | 2022-03-04 | 2022-03-18 | 0% | Masha and Hemaswi
12 |  |  | 1.04 | Admin Login | Add text fields for a user to add their password | 2022-03-04 | 2022-03-18 | 0% | Masha and Hemaswi
13 |  |  | 1.04 | Admin Login | Add login button | 2022-03-04 | 2022-03-18 | 0% | Masha and Hemaswi
14 |  |  | 1.04 | Admin Login | Develop test cases for GUI, core functionality, and crosscuts | 2022-03-04 | 2022-03-18 | 0% | Abhilash and Brinda
15 |  |  | 1.04 | Admin Login | Complete Test cases | 2022-03-04 | 2022-03-18 | 0% | Abhilash and Brinda
16 |  | 02. Menu Management | 2.03 | Set pick up times | Implement core features and entitlements crosscuts | 2022-03-18 | 2022-04-01 | 0% | Masha and Hemaswi
17 |  |  | 2.03 | Set pick up times | Implement data flow out crosscuts | 2022-03-18 | 2022-04-01 | 0% | Masha and Hemaswi
18 |  |  | 2.03 | Set pick up times | Add a button to edit the hours for pick up times. | 2022-03-18 | 2022-04-01 | 0% | Masha and Hemaswi
19 |  |  | 2.03 | Set pick up times | Add text fields so user can input pick up time hours | 2022-03-18 | 2022-04-01 | 0% | Masha and Hemaswi
20 |  |  | 2.03 | Set pick up times | Develop test cases for GUI, core functionality, and crosscuts | 2022-03-18 | 2022-04-01 | 0% | Abhilash and Brinda
21 |  |  | 2.03 | Set pick up times | Execute test cases | 2022-03-18 | 2022-04-01 | 0% | Abhilash and Brinda
22 |  | 03. Order & cart management | 3.15 | Choose pick up times | Implement crosscut core functionality and entitlements | 2022-03-18 | 2022-04-01 | 0% | Masha and Hemaswi
23 |  |  | 3.15 | Choose pick up times | Implement data flow out crosscuts | 2022-03-18 | 2022-04-01 | 0% | Masha and Hemaswi
24 |  |  | 3.15 | Choose pick up times | Add a dropdown box that will allow a user to choose one of the pick up times available | 2022-03-18 | 2022-04-01 | 0% | Masha and Hemaswi
25 |  |  | 3.15 | Choose pick up times | Develop test cases for GUI, core functionality, and crosscuts | 2022-03-18 | 2022-04-01 | 0% | Abhilash and Brinda
26 |  |  | 3.15 | Choose pick up times | Execute test cases | 2022-03-18 | 2022-04-01 | 0% | Abhilash and Brinda